## Sheet1
Risk | Effect | Cause | Probability | Severity | Mitigating Actions | Review
Project Level Threats
Project Not Finished on Time | Failure to complete the project on time will lead to a lower quality product. A lower quality product will inevitably lead to a lower overall mark. | Not completing tasks in the expected timeframe. Over-engineering of the site. Shifting Deadlines | 3 | 3 | Ensure that all planned features/tasks can be completed in a reasonable, project specific timeframe. Allow for shifting deadlines by providing the MVP before adding other features. Attempt to create a buffer, aiming to have the project completed in advance of the deadline. | Due to a deadline being brought forward, certain site functionality had to be sacrificed. Thankfully, careful preparation ensured that the MVP was delivered.
Project Doesn't Match Criteria | Failure to match the core criteria of the project will result in a product that doesn't do what it needs to. This would impact the marks received for the project overall. | Misunderstanding of project brief. Malfunctioning of the code. | 1 | 4 | Ensure that the project criteria is thoroughly read and understood. Refer back to the briefing document at regular intervals throughout the project, in case something may have been overlooked. | Thankfully, this issue did not arise due to regular close inspection of the project specification document.
Personal Unavailability to Continue working on Project | Inability to complete the project for any personal reason would cause the immediate halt to further coding/documentation, thereby putting the project into a state of 'statis' until my return. | Illness. Injury. Family emergencies. | 2 | 5 | Due to the unpredictable nature of this particular risk, no meaningful mitigating actions can be taken other than making every effort to get the project completed as quickly as possible, with an emphasis on producing the MVP. | This issue did not arise during the project.
Application Threats
CRUD Features Not Functioning | As this application is based entirely around CRUD features, if this risk were to come to pass then the application would be all but useless. | Improperly initialised database. Mistake or mistakes within the codebase. | 3 | 4 | The use of extenisve testing and a test driven approach allows for significant mitigation of this risk. | Due to the test driven approach used in during the project, this risk only materialised briefly, and usually as a result of small typos. As a result of the frequency of manual testing, no functionality was ever non-functional for long.
Unauthorised Data Manipulation Allowed | Allowing an unauthorised user to manipulate the data within the database could entirely corrupt an instance of the application, necessitating a full restart of the database. | Improper authentication implementation. SQL Injection attack. | 2 | 4 | To ensure the integrity of the database, the authentication system must be properly implemented, without any errors. Protection against SQL Injection attacks was considered, but due to the small nature of this project was not implemented. | The authentication system appears at present to be air-tight, with no errors occurring throughout all of the project's manual and automated tests.
Users Unable to Log In | Inability to log in will render the site next to useless for users, as no CRUD functionality can take place without first being authorised. | Improper authentication implementation. | 1 | 4 | The authentication system is the backbone of the website, and as such must be implemented properly and must work every time it's needed. To achieve this, Flask-Login, a popular and secure authentication library was used. | Flask-Login performed as expected from its first implementation. The only issue which arose from the use of the library was that my coverage reports could not reach 100%, as some of the code required to use the authentication system was untestable.
User Threats
Accidental Recipe Deletion | Deleting a recipe accidentally will waste the users time and effort. | Unguarded deletion functionality. | 3 | 1 | Implementing a modal which asks the user to confirm deletion essentially eliminates the possibility of accidental deletion, except in the case of user who is determined to be careless. | The modal solution worked well, and as expected makes it difficult to accidentally delete a recipe.
User 2 Updating/Deleting User 1's Recipes | If a user can update/delete the recipe of another user, chaos will befall the site as no recipe will be safe from interference. | Insufficiently guarded update/delete routes. | 1 | 3 | Ensure that the backend checks that a user is the author of a recipe before allowing that user to update or delete the recipe. | In practice, only a user with malicious intent would be likely to update/delete another user's recipes, due to the front end button visibility settings. (Users only see update/delete buttons on their own recipes) A user could however enter the update/delete route for a recipe, thereby bypassing the front-end protection. Therefore, it was necessary to implement a backend clause that checked that a user was a recipe's author before allowing them to update/delete a recipe.